## Cover
REQUIREMENTS TRACEABILITY MATRIX (RTM)
Flipkart Website – Desktop Web ¦ v1.0 ¦ 19-Mar-2026
Project | Flipkart Website (Desktop Web)
Application URL | https://www.flipkart.com
Document Type | Requirements Traceability Matrix (RTM)
Test Report Reference | Flipkart_Manual_Testing_Report_v1.xlsx
Prepared By | Gurupadeshwar
Reviewed By | QA Lead
Date | 19-Mar-2026
Version | v1.0
Total Requirements | 74
Total Test Cases | 74
Requirements Covered | 74 / 74 (100%)
Overall Test Status | PASS – All 74 TCs Passed, 0 Bugs Found
Testing Types Used | Functional ¦ Integration ¦ Usability ¦ Security
Testing Type Legend
Functional | Tests that verify a specific feature or function behaves according to requirements
Integration | Tests that verify two or more modules/components work together correctly
Usability | Tests that verify the UI layout, look-and-feel, user experience and visual consistency
Security | Tests that verify authentication, session management and access-control behaviour

## RTM
Flipkart Website – Requirements Traceability Matrix (RTM)
Requirement ID | Module | Requirement Description | Test Case ID | Test Case Description | Testing Type | Test Scenario ID | Priority | Test Status | Defect ID
REQ_001 | Home Page | Home Page | TC_HP_001 | Validate the Flipkart logo is visible and redirects to the Home Page from any inner page | Functional | TS_001 | High | Pass | N/A
REQ_002 | Home Page | Home Page | TC_HP_002 | Validate the category navigation bar displays all primary categories | Functional | TS_001 | High | Pass | N/A
REQ_003 | Home Page | Home Page | TC_HP_003 | Validate the Home Page banner carousel auto-scrolls and manual navigation works | Usability | TS_001 | Medium | Pass | N/A
REQ_004 | Home Page | Home Page | TC_HP_004 | Validate the Deal of the Day section displays products with countdown timers, MRP and discount % | Functional | TS_001 | Medium | Pass | N/A
REQ_005 | Home Page | Home Page | TC_HP_005 | Validate personalised product recommendations are shown for a logged-in user | Functional | TS_001 | Medium | Pass | N/A
REQ_006 | Login / Signup | Login / Signup | TC_LF_001 | Validate the Login modal/page is accessible by clicking the Login button in the header | Functional | TS_002 | Critical | Pass | N/A
REQ_007 | Login / Signup | Login / Signup | TC_LF_002 | Validate login with a registered mobile number and correct OTP | Functional | TS_002 | Critical | Pass | N/A
REQ_008 | Login / Signup | Login / Signup | TC_LF_003 | Validate login with a registered email address and correct password | Functional | TS_002 | Critical | Pass | N/A
REQ_009 | Login / Signup | Login / Signup | TC_LF_004 | Validate login with an incorrect password shows an error message and does not log the user in | Security | TS_002 | Critical | Pass | N/A
REQ_010 | Login / Signup | Login / Signup | TC_LF_005 | Validate new user signup with mobile number, OTP and registration form | Functional | TS_002 | Critical | Pass | N/A
REQ_011 | Login / Signup | Login / Signup | TC_LF_006 | Validate login form shows validation error when the mobile/email field is submitted empty | Functional | TS_002 | High | Pass | N/A
REQ_012 | Login / Signup | Login / Signup | TC_LF_007 | Validate login with an invalid format mobile number (less than 10 digits) shows an error | Functional | TS_002 | High | Pass | N/A
REQ_013 | Login / Signup | Login / Signup | TC_LF_008 | Validate user session is maintained after browser page refresh | Security | TS_002 | High | Pass | N/A
REQ_014 | Search Functionality | Search Functionality | TC_SF_001 | Validate searching for an existing product by name returns relevant results | Functional | TS_003 | High | Pass | N/A
REQ_015 | Search Functionality | Search Functionality | TC_SF_002 | Validate auto-suggestions appear while typing in the search bar | Functional | TS_003 | High | Pass | N/A
REQ_016 | Search Functionality | Search Functionality | TC_SF_003 | Validate searching for a non-existent product shows a no-results message | Functional | TS_003 | Medium | Pass | N/A
REQ_017 | Search Functionality | Search Functionality | TC_SF_004 | Validate that search is case-insensitive | Functional | TS_003 | Medium | Pass | N/A
REQ_018 | Search Functionality | Search Functionality | TC_SF_005 | Validate search results display product cards with all key details (image, name, price, discount, rating) | Usability | TS_003 | High | Pass | N/A
REQ_019 | Search Functionality | Search Functionality | TC_SF_006 | Validate that Brand filter on the search results page narrows results correctly | Functional | TS_003 | High | Pass | N/A
REQ_020 | Product Listing Page | Product Listing Page | TC_PLP_001 | Validate navigating to a category page from the navigation bar shows relevant products | Functional | TS_004 | High | Pass | N/A
REQ_021 | Product Listing Page | Product Listing Page | TC_PLP_002 | Validate the total product count is displayed and updates dynamically on the listing page | Functional | TS_004 | Medium | Pass | N/A
REQ_022 | Product Listing Page | Product Listing Page | TC_PLP_003 | Validate Sort by 'Price: Low to High' reorders products correctly | Functional | TS_004 | High | Pass | N/A
REQ_023 | Product Listing Page | Product Listing Page | TC_PLP_004 | Validate the Brand filter narrows results to the selected brand and shows a filter chip | Functional | TS_004 | High | Pass | N/A
REQ_024 | Product Listing Page | Product Listing Page | TC_PLP_005 | Validate the Price Range filter displays only products within the specified range | Functional | TS_004 | High | Pass | N/A
REQ_025 | Product Listing Page | Product Listing Page | TC_PLP_006 | Validate the Customer Rating filter shows only products with the selected rating or above | Functional | TS_004 | Medium | Pass | N/A
REQ_026 | Product Listing Page | Product Listing Page | TC_PLP_007 | Validate clicking a product card on the PLP navigates to the correct Product Display Page | Integration | TS_004 | High | Pass | N/A
REQ_027 | Product Display Page | Product Display Page | TC_PDP_001 | Validate product title, brand, MRP, selling price and discount % are displayed on PDP | Functional | TS_005 | High | Pass | N/A
REQ_028 | Product Display Page | Product Display Page | TC_PDP_002 | Validate multiple product images are displayed and thumbnail navigation updates the main image | Usability | TS_005 | High | Pass | N/A
REQ_029 | Product Display Page | Product Display Page | TC_PDP_003 | Validate the customer ratings and review count are displayed on PDP | Functional | TS_005 | Medium | Pass | N/A
REQ_030 | Product Display Page | Product Display Page | TC_PDP_004 | Validate EMI options are displayed for eligible high-value products on PDP | Functional | TS_005 | Medium | Pass | N/A
REQ_031 | Product Display Page | Product Display Page | TC_PDP_005 | Validate the estimated delivery date is shown on PDP after pincode entry | Functional | TS_005 | High | Pass | N/A
REQ_032 | Product Display Page | Product Display Page | TC_PDP_006 | Validate ADD TO CART button adds the product to the cart and updates the header cart badge | Integration | TS_005 | Critical | Pass | N/A
REQ_033 | Product Display Page | Product Display Page | TC_PDP_007 | Validate BUY NOW button takes the user directly to the checkout flow | Integration | TS_005 | Critical | Pass | N/A
REQ_034 | Wishlist | Wishlist | TC_WL_001 | Validate adding a product to Wishlist from the Product Display Page | Functional | TS_006 | High | Pass | N/A
REQ_035 | Wishlist | Wishlist | TC_WL_002 | Validate adding a product to Wishlist from the Product Listing Page | Functional | TS_006 | High | Pass | N/A
REQ_036 | Wishlist | Wishlist | TC_WL_003 | Validate removing a product from the Wishlist updates the list immediately | Functional | TS_006 | Medium | Pass | N/A
REQ_037 | Wishlist | Wishlist | TC_WL_004 | Validate Move to Cart button on the Wishlist page moves the product to the Cart | Integration | TS_006 | High | Pass | N/A
REQ_038 | Wishlist | Wishlist | TC_WL_005 | Validate Wishlist contents are preserved after logout and re-login | Functional | TS_006 | Medium | Pass | N/A
REQ_039 | Cart | Cart | TC_CT_001 | Validate the Cart page displays added products with correct name, qty, seller and price | Functional | TS_007 | Critical | Pass | N/A
REQ_040 | Cart | Cart | TC_CT_002 | Validate the cart price summary (MRP, discount, delivery, total) is calculated correctly | Functional | TS_007 | Critical | Pass | N/A
REQ_041 | Cart | Cart | TC_CT_003 | Validate removing a product from the cart updates the cart total correctly | Functional | TS_007 | High | Pass | N/A
REQ_042 | Cart | Cart | TC_CT_004 | Validate Save for Later moves a product to the saved section outside the active cart | Functional | TS_007 | Medium | Pass | N/A
REQ_043 | Cart | Cart | TC_CT_005 | Validate applying a valid coupon code reduces the cart total immediately | Functional | TS_007 | High | Pass | N/A
REQ_044 | Cart | Cart | TC_CT_006 | Validate Place Order button on the Cart page navigates to the checkout address step | Integration | TS_007 | Critical | Pass | N/A
REQ_045 | Checkout | Checkout | TC_CO_001 | Validate the checkout page redirects an unauthenticated user to the Login page | Security | TS_008 | Critical | Pass | N/A
REQ_046 | Checkout | Checkout | TC_CO_002 | Validate the saved default address is pre-selected at the checkout address step | Functional | TS_008 | High | Pass | N/A
REQ_047 | Checkout | Checkout | TC_CO_003 | Validate the user can add a new delivery address during checkout | Functional | TS_008 | High | Pass | N/A
REQ_048 | Checkout | Checkout | TC_CO_004 | Validate UPI payment option successfully places the order and shows Order Confirmation | Integration | TS_008 | Critical | Pass | N/A
REQ_049 | Checkout | Checkout | TC_CO_005 | Validate Cash on Delivery (COD) payment option places the order successfully | Integration | TS_008 | High | Pass | N/A
REQ_050 | Checkout | Checkout | TC_CO_006 | Validate Credit/Debit Card payment processes and shows Order Confirmation page | Integration | TS_008 | Critical | Pass | N/A
REQ_051 | Checkout | Checkout | TC_CO_007 | Validate Flipkart Pay Later option places the order for eligible accounts | Integration | TS_008 | High | Pass | N/A
REQ_052 | Checkout | Checkout | TC_CO_008 | Validate SuperCoins can be applied at checkout to reduce the payable amount | Integration | TS_008 | High | Pass | N/A
REQ_053 | Order Management | Order Management | TC_OM_001 | Validate the Order History page lists all past orders with date, summary, price and status | Functional | TS_009 | High | Pass | N/A
REQ_054 | Order Management | Order Management | TC_OM_002 | Validate clicking on an order opens the Order Details page with complete information | Functional | TS_009 | High | Pass | N/A
REQ_055 | Order Management | Order Management | TC_OM_003 | Validate Ekart delivery tracking is accessible for an order in Out for Delivery status | Integration | TS_009 | High | Pass | N/A
REQ_056 | Order Management | Order Management | TC_OM_004 | Validate order cancellation is possible before the order is shipped | Functional | TS_009 | High | Pass | N/A
REQ_057 | Order Management | Order Management | TC_OM_005 | Validate the Cancel option is not available for already-shipped or delivered orders | Functional | TS_009 | Medium | Pass | N/A
REQ_058 | Order Management | Order Management | TC_OM_006 | Validate My Orders page shows No Orders message for a new account with no history | Functional | TS_009 | Low | Pass | N/A
REQ_059 | Returns & Replacement | Returns & Replacement | TC_RE_001 | Validate return request can be initiated for a delivered item within the return window | Functional | TS_010 | High | Pass | N/A
REQ_060 | Returns & Replacement | Returns & Replacement | TC_RE_002 | Validate the Return option is not available after the return window has expired | Functional | TS_010 | High | Pass | N/A
REQ_061 | Returns & Replacement | Returns & Replacement | TC_RE_003 | Validate replacement request can be initiated for a defective delivered item | Functional | TS_010 | High | Pass | N/A
REQ_062 | Returns & Replacement | Returns & Replacement | TC_RE_004 | Validate refund status and expected credit date are visible after return is picked up | Functional | TS_010 | High | Pass | N/A
REQ_063 | Returns & Replacement | Returns & Replacement | TC_RE_005 | Validate that non-returnable products do not show a Return option and display a label | Functional | TS_010 | High | Pass | N/A
REQ_064 | My Account | My Account | TC_MA_001 | Validate My Account page displays the user's name and masked registered mobile number | Functional | TS_011 | Medium | Pass | N/A
REQ_065 | My Account | My Account | TC_MA_002 | Validate the user can add a new delivery address from the Manage Addresses section | Functional | TS_011 | High | Pass | N/A
REQ_066 | My Account | My Account | TC_MA_003 | Validate SuperCoins balance and earned history are displayed in My Account | Functional | TS_011 | Medium | Pass | N/A
REQ_067 | My Account | My Account | TC_MA_004 | Validate Flipkart Plus membership tier and benefits are displayed for Plus members | Functional | TS_011 | Medium | Pass | N/A
REQ_068 | My Account | My Account | TC_MA_005 | Validate the user can edit their profile name and the update is saved successfully | Functional | TS_011 | Medium | Pass | N/A
REQ_069 | My Account | My Account | TC_MA_006 | Validate logout from the profile menu terminates the session and reverts header to Login | Security | TS_011 | High | Pass | N/A
REQ_070 | Header & Footer | Header & Footer | TC_HF_001 | Validate the Flipkart header contains all required elements for unauthenticated users | Usability | TS_012 | High | Pass | N/A
REQ_071 | Header & Footer | Header & Footer | TC_HF_002 | Validate the Cart icon badge in the header reflects the correct item count in real time | Functional | TS_012 | High | Pass | N/A
REQ_072 | Header & Footer | Header & Footer | TC_HF_003 | Validate the category navigation bar links navigate to the correct listing pages | Functional | TS_012 | High | Pass | N/A
REQ_073 | Header & Footer | Header & Footer | TC_HF_004 | Validate all footer links navigate to their correct respective pages | Functional | TS_012 | Medium | Pass | N/A
REQ_074 | Header & Footer | Header & Footer | TC_HF_005 | Validate the Download App links in the footer open the correct app store pages | Functional | TS_012 | Low | Pass | N/A

## Testing Type Summary
Testing Type Distribution – Flipkart RTM
Testing Type | No. of TCs | % of Total | TC IDs | All Passed | Defects
Functional | 55 | 74.3% | TC_HP_001, TC_HP_002, TC_HP_004, TC_HP_005, TC_LF_001, TC_LF_002, TC_LF_003, TC_LF_005, TC_LF_006, TC_LF_007, TC_SF_001, TC_SF_002, TC_SF_003, TC_SF_004, TC_SF_006, TC_PLP_001, TC_PLP_002, TC_PLP_003, TC_PLP_004, TC_PLP_005, TC_PLP_006, TC_PDP_001, TC_PDP_003, TC_PDP_004, TC_PDP_005, TC_WL_001, TC_WL_002, TC_WL_003, TC_WL_005, TC_CT_001, TC_CT_002, TC_CT_003, TC_CT_004, TC_CT_005, TC_CO_002, TC_CO_003, TC_OM_001, TC_OM_002, TC_OM_004, TC_OM_005, TC_OM_006, TC_RE_001, TC_RE_002, TC_RE_003, TC_RE_004, TC_RE_005, TC_MA_001, TC_MA_002, TC_MA_003, TC_MA_004, TC_MA_005, TC_HF_002, TC_HF_003, TC_HF_004, TC_HF_005 | Yes ✓ | 0
Integration | 11 | 14.9% | TC_PLP_007, TC_PDP_006, TC_PDP_007, TC_WL_004, TC_CT_006, TC_CO_004, TC_CO_005, TC_CO_006, TC_CO_007, TC_CO_008, TC_OM_003 | Yes ✓ | 0
Usability | 4 | 5.4% | TC_HP_003, TC_SF_005, TC_PDP_002, TC_HF_001 | Yes ✓ | 0
Security | 4 | 5.4% | TC_LF_004, TC_LF_008, TC_CO_001, TC_MA_006 | Yes ✓ | 0
TOTAL | 74 | 100% |  | 74 / 74 | 0
Module-wise Testing Type Breakdown
Module | Functional | Integration | Usability | Security | Total TCs
Home Page | 4 | - | 1 | - | 5
Login / Signup | 6 | - | - | 2 | 8
Search Functionality | 5 | - | 1 | - | 6
Product Listing Page | 6 | 1 | - | - | 7
Product Display Page | 4 | 2 | 1 | - | 7
Wishlist | 4 | 1 | - | - | 5
Cart | 5 | 1 | - | - | 6
Checkout | 2 | 5 | - | 1 | 8
Order Management | 5 | 1 | - | - | 6
Returns & Replacement | 5 | - | - | - | 5
My Account | 5 | - | - | 1 | 6
Header & Footer | 4 | - | 1 | - | 5
TOTAL | 55 | 11 | 4 | 4 | 74

## Module Summary
Module-wise RTM Summary – Flipkart Website
Module | Scenario ID | No. of TCs | Passed | Failed | Requirement Coverage | Testing Types Used
Home Page | TS_001 | 5 | 5 | 0 | 100% | Functional, Usability
Login / Signup | TS_002 | 8 | 8 | 0 | 100% | Functional, Security
Search Functionality | TS_003 | 6 | 6 | 0 | 100% | Functional, Usability
Product Listing Page | TS_004 | 7 | 7 | 0 | 100% | Functional, Integration
Product Display Page | TS_005 | 7 | 7 | 0 | 100% | Functional, Integration, Usability
Wishlist | TS_006 | 5 | 5 | 0 | 100% | Functional, Integration
Cart | TS_007 | 6 | 6 | 0 | 100% | Functional, Integration
Checkout | TS_008 | 8 | 8 | 0 | 100% | Functional, Integration, Security
Order Management | TS_009 | 6 | 6 | 0 | 100% | Functional, Integration
Returns & Replacement | TS_010 | 5 | 5 | 0 | 100% | Functional
My Account | TS_011 | 6 | 6 | 0 | 100% | Functional, Security
Header & Footer | TS_012 | 5 | 5 | 0 | 100% | Functional, Usability
TOTAL | TS_001–TS_012 | 74 | 74 | 0 | 100%