## Test Closure Report
TEST CLOSURE REPORT – Flipkart Website (Desktop Web)
Project: Flipkart.com ¦ Version: v1.0 ¦ Date: 19-Mar-2026
1. Document Information
Document ID | FK-CL-001
Project | Flipkart Website (Desktop Web)
Application URL | https://www.flipkart.com
Test Cycle | Manual Testing Cycle 1 ¦ v1.0
Execution Period | 17-Mar-2026 to 18-Mar-2026
Closure Date | 19-Mar-2026
Prepared By | Gurupadeshwar
Reviewed By | QA Lead
Approved By | QA Manager
2. Test Execution Summary
Total Test Scenarios | 12
Total Test Cases Planned | 74
Total Test Cases Executed | 74
Total Test Cases Passed | 74
Total Test Cases Failed | 0
Total Test Cases Blocked | 0
Total Test Cases Not Run | 0
Pass Percentage | 100.00%
Fail Percentage | 0.00%
Total Defects Raised | 0
Critical Defects | 0
High Severity Defects | 0
Medium / Minor Defects | 0
All Defects Resolved | N/A – No defects raised in this cycle
3. Module-wise Closure Summary
Module | TCs Executed | Passed | Failed | Pass % | Coverage
Home Page | 5 | 5 | 0 | 100% | 100%
Login & Signup | 8 | 8 | 0 | 100% | 100%
Search Functionality | 6 | 6 | 0 | 100% | 100%
Product Listing Page | 7 | 7 | 0 | 100% | 100%
Product Display Page | 7 | 7 | 0 | 100% | 100%
Wishlist | 5 | 5 | 0 | 100% | 100%
Cart | 6 | 6 | 0 | 100% | 100%
Checkout | 8 | 8 | 0 | 100% | 100%
Order Management | 6 | 6 | 0 | 100% | 100%
Returns & Replacement | 5 | 5 | 0 | 100% | 100%
My Account | 6 | 6 | 0 | 100% | 100%
Header & Footer | 5 | 5 | 0 | 100% | 100%
TOTAL | 74 | 74 | 0 | 100% | 100%
4. Testing Type Coverage
Testing Type | TCs | % of Total | All Passed | Defects
Functional | 55 | 74.3% | Yes ✓ | 0
Integration | 11 | 14.9% | Yes ✓ | 0
Usability | 4 | 5.4% | Yes ✓ | 0
Security | 4 | 5.4% | Yes ✓ | 0
5. Defect Summary
Total Defects Raised | 0 – No functional defects were identified during this test execution cycle.
Defect Report | No Bug Report sheet has been generated. If defects are identified in a subsequent regression cycle, a Defect Report will be produced as a separate STLC deliverable (FK-DR-002).
Defect Leakage | 0% – No known defects escaped to production during this test cycle.
6. STLC Deliverables Completion Status
# | Deliverable | Document ID | Status | Owner
1 | Test Plan | FK-TP-001 | ✔ Completed | QA Engineer / QA Lead
2 | Test Scenarios (12 scenarios) | FK-TS-001 | ✔ Completed | QA Engineer / QA Lead
3 | Test Cases (74 test cases) | FK-TC-001 | ✔ Completed | QA Engineer / QA Lead
4 | Requirements Traceability Matrix (RTM) | FK-RTM-001 | ✔ Completed | QA Engineer / QA Lead
5 | Test Data Sheet | FK-TD-001 | ✔ Completed | QA Engineer / QA Lead
6 | Test Environment Setup Checklist | FK-ENV-001 | ✔ Completed | QA Engineer / QA Lead
7 | Test Execution Report / Log | FK-EX-001 | ✔ Completed | QA Engineer / QA Lead
8 | Defect Report | FK-DR-001 | N/A – 0 Defects | QA Engineer / QA Lead
9 | Test Summary Report | FK-SR-001 | ✔ Completed | QA Engineer / QA Lead
10 | Test Closure Report | FK-CL-001 | ✔ Completed | QA Engineer / QA Lead
7. Lessons Learned
What went well | • All 74 planned test cases were executed within the 2-day schedule • Test environment was stable throughout the execution cycle • Clear requirement coverage (100%) was achieved through the RTM • No critical defects were raised, indicating a stable application build • Cross-browser testing on Chrome, Firefox and Safari was completed without environment issues
What could be improved | • Payment testing on production requires carefully managed test scenarios to avoid inadvertently placing real orders • Coupon codes expire; test data should be refreshed at the start of each execution day • A staging/UAT environment would be preferable to production for destructive tests
Recommendations | • Schedule a regression test cycle after each major Flipkart release • Add automated smoke test suite for critical paths (Login, Add to Cart, Checkout) • Maintain a dedicated test account with consistent order history for regression use • Extend scope in next cycle to include Grocery category and Two Wheelers module
8. Exit Criteria Verification
Exit Criterion | Target | Actual | Met?
All planned test cases executed | 74 / 74 | 74 / 74 (100%) | ✔ Yes
Pass rate ≥ 95% | ≥ 95% | 100% | ✔ Yes
No Critical defects open | 0 Critical | 0 Critical | ✔ Yes
No High defects open | 0 High | 0 High | ✔ Yes
All STLC deliverables completed | 10 documents | 10 documents | ✔ Yes
Test Summary Report signed off | Signed off | Signed off | ✔ Yes
9. Sign-off & Approval
Role | Name | Signature | Decision | Date | Remarks
QA Engineer | Gurupadeshwar | ______________________ | Approved | 19-Mar-2026 | All exit criteria met. Test closure approved.
QA Lead |  | ______________________ | Approved | 19-Mar-2026 | All exit criteria met. Test closure approved.
QA Manager |  | ______________________ | Approved | 19-Mar-2026 | All exit criteria met. Test closure approved.