## Test Plan
TEST PLAN – Flipkart Website (Desktop Web)
Project: Flipkart.com ¦ Version: v1.0 ¦ Date: 19-Mar-2026
1. Document Information
Document Title | Test Plan – Flipkart Website Manual Testing
Document ID | FK-TP-001
Version | v1.0
Prepared By | Gurupadeshwar
Reviewed By | QA Lead
Approved By | QA Manager
Date Created | 19-Mar-2026
Last Updated | 19-Mar-2026
Application Under Test | https://www.flipkart.com (Desktop Web)
2. Test Objective
The objective of this Test Plan is to define the strategy, scope, approach, resources, schedule and deliverables for the manual testing of the Flipkart website (Desktop Web). This document ensures that all functional requirements of Flipkart.com are tested systematically, all test activities are planned and tracked, and the quality of the application is validated before a release sign-off is given.
3. Scope of Testing
IN SCOPE
✔ Home Page – logo, navigation bar, banner carousel, deal sections, personalised recommendations
✔ Login & Signup – mobile OTP login, email/password login, new user registration, session management
✔ Search Functionality – keyword search, auto-suggestions, no-results state, case-insensitivity, filters
✔ Product Listing Page (PLP) – category navigation, sort, brand/price/rating filters, product count
✔ Product Display Page (PDP) – product details, images, ratings, EMI, delivery estimate, Add to Cart, Buy Now
✔ Wishlist – add from PDP/PLP, remove, Move to Cart, persistence after re-login
✔ Cart – product display, price summary, remove, Save for Later, coupon application, Place Order
✔ Checkout – address management, UPI, COD, Credit/Debit Card, Pay Later, SuperCoins redemption
✔ Order Management – order history, order details, Ekart tracking, cancellation
✔ Returns & Replacement – initiate return/replace, return window enforcement, refund status
✔ My Account – profile, address book, SuperCoins balance, Flipkart Plus membership, logout
✔ Header & Footer – all header elements, cart badge, nav bar, footer links, app download links
OUT OF SCOPE
✘ Mobile App testing (Android / iOS) – out of scope for this test cycle
✘ Seller Portal / Flipkart Seller Hub – not part of this test cycle
✘ Backend / API-level testing – not part of manual testing scope
✘ Performance / Load testing under concurrent user scenarios
✘ Automated regression testing
✘ Flipkart Ads / Sponsored listings management
4. Test Approach
Testing Methodology | Manual Black-Box Testing. Test cases are designed from the user's perspective without access to internal source code. All testing is performed on the live production environment at https://www.flipkart.com.
Test Design Techniques | Equivalence Partitioning, Boundary Value Analysis, Error Guessing, Decision Table Testing, Use-Case Based Testing
Testing Types | Functional Testing ¦ Integration Testing ¦ Usability Testing ¦ Security Testing
Test Levels | System Testing (end-to-end flows) and User Acceptance Testing (UAT)-style validation
Entry Criteria | 1. Application is accessible at https://www.flipkart.com 2. Test environment checklist is signed off 3. All test cases are reviewed and approved 4. Test data (accounts, products, payment methods) is ready
Exit Criteria | 1. All 74 planned test cases are executed 2. Pass rate ≥ 95% 3. No Critical or High severity defects are open 4. Test Summary Report is signed off by QA Lead
Suspension Criteria | Testing is suspended if: application is inaccessible for > 2 hours, or if > 30% of test cases are blocked due to environment issues
Resumption Criteria | Testing resumes when: environment is restored and confirmed stable, and blocked test cases can be re-executed
5. Test Schedule
Phase | Activity | Start Date | End Date | Duration | Owner
Phase 1 – Requirement Analysis | Review requirements, identify testable features | 10-Mar-2026 | 11-Mar-2026 | 2 days | QA Engineer
Phase 2 – Test Planning | Create Test Plan, define scope and schedule | 12-Mar-2026 | 12-Mar-2026 | 1 day | QA Lead
Phase 3 – Test Case Development | Write Test Scenarios, Test Cases, RTM, Test Data | 13-Mar-2026 | 15-Mar-2026 | 3 days | QA Engineer
Phase 4 – Env. Setup & Review | Configure browsers, prepare test accounts and data | 16-Mar-2026 | 16-Mar-2026 | 1 day | QA Engineer
Phase 5 – Test Execution | Execute all 74 manual test cases, log results | 17-Mar-2026 | 18-Mar-2026 | 2 days | QA Engineer
Phase 6 – Defect Reporting | Log, classify and track any defects found | 17-Mar-2026 | 18-Mar-2026 | Ongoing | QA Engineer
Phase 7 – Test Closure | Prepare Test Summary, Closure Report, sign off | 19-Mar-2026 | 19-Mar-2026 | 1 day | QA Lead
6. Resources
Resource | Role | Responsibility | Tools / Skills Required | Availability
QA Engineer | Test Execution | Write and execute test cases, log results, report defects | Manual Testing, Chrome/Firefox/Safari, Excel | 100%
QA Lead | Test Management | Review test plan, test cases and RTM; sign off on deliverables | Test Management, STLC, Risk Analysis | 50%
QA Manager | Sign-off | Final approval of Test Plan and Test Closure Report | QA Governance | 20%
Developer | Defect Support | Clarify requirements, fix any confirmed defects | Flipkart Web Application | On-demand
7. Test Deliverables
# | Deliverable | Description | Status | Owner
1 | Test Plan | This document – FK-TP-001 | Completed | QA Lead
2 | Test Scenarios | 12 test scenarios covering all modules | Completed | QA Engineer
3 | Test Cases | 74 detailed test cases with steps and expected results | Completed | QA Engineer
4 | Requirements Traceability Matrix (RTM) | 74 requirements mapped to test cases with testing type | Completed | QA Engineer
5 | Test Data Sheet | Test accounts, product data and payment methods used | Completed | QA Engineer
6 | Test Environment Checklist | Browser/OS matrix and setup verification | Completed | QA Engineer
7 | Test Execution Report / Log | Daily execution log with pass/fail results per TC | Completed | QA Engineer
8 | Defect Report | Log of all confirmed defects (0 defects in this cycle) | Completed | QA Engineer
9 | Test Summary Report | Final execution summary and sign-off | Completed | QA Lead
10 | Test Closure Report | STLC closure with lessons learned and metrics | Completed | QA Lead
8. Risks & Mitigations
# | Risk | Likelihood | Impact | Mitigation
1 | Live production site content changes (prices, promotions) during test execution | Medium | Low | Note observation timestamps; re-test price-specific TCs on same day
2 | Test user account gets locked due to multiple OTP attempts | Low | Medium | Maintain 2 registered test accounts; stagger OTP tests
3 | Payment gateway not accessible in test/sandbox mode on production | Medium | High | Use test card numbers where possible; document expected flows for payment TCs
4 | Flipkart UI changes or A/B tests alter expected UI elements | Medium | Medium | Document baseline UI with screenshots; flag UI deviations as observations, not defects
5 | Network instability causing intermittent page load failures | Low | Low | Retest failed TCs at least once; use stable broadband connection
9. Approvals
Role | Name | Signature | Date
QA Engineer | Gurupadeshwar | _______________________ | ___________
QA Lead |  | _______________________ | ___________
QA Manager |  | _______________________ | ___________