## Bug Report
Bug Report – OrangeHRM Open Source v5.8 ¦ My Info (ESS) Module ¦ 19-Mar-2026
Application: https://opensource-demo.orangehrmlive.com ¦ Credentials: Admin / admin123 ¦ ESS User: pavan@12345 / pavan@12345 ¦ Reported By: QA Engineer ¦ Total Bugs: 3
Bug ID | Module | TC ID | Req ID | Severity | Priority | Description | Steps to Reproduce | Status | Assigned To | Fixed Date
OHRM_BUG_001 | My Info (ESS) – Photograph Upload | TC_ESS_007 | REQ_072 | S2 – High | S2 – High | When an ESS user uploads a .exe file as their photograph, the entire file is sent to the server before the 'Invalid file type' error is shown. Client-side validation must reject unsupported files (only JPG, GIF, PNG allowed) before any upload begins. | 1. Login as ESS user 2. Go to MyInfo → Click on the profile photograph 3. Click Browse → select a .exe file 4. Click Upload → File uploads completely to server, THEN error is shown | Open | Dev Team Lead | —
OHRM_BUG_002 | My Info (ESS) – Personal Details | TC_ESS_006 | REQ_071 | S4 – Low | S4 – Low | The 'SSN No' field is listed in requirements as a restricted (read-only) field on the My Info > Personal Details page. However, the field is completely absent from the page. Clarification needed: intentional removal or defect? | 1. Login as ESS user 2. Click MyInfo → Personal Details 3. Click Edit → SSN No field is not visible in view mode or edit mode | Clarification Needed | Product Owner | —
Total | S2 – High | S4 – Low | Open | InProgress | Clarification Needed
2 | 1 | 1 | 1 | 1 | 1